## How-To
BLAMELESS POSTMORTEM - HOW TO USE
What this workbook is
A template for a blameless postmortem: a summary with timestamps and calculated response times, a timeline, contributing factors, and tracked action items.
Educational template. It supports a software or IT team's review and planning. It is not security, legal, compliance, or engineering advice and does not replace your organization's policies and controls. Avoid entering customer data, credentials, or other sensitive information.
Steps
1. Incident Summary: describe the incident and enter the five timestamps (impact start, detected, acknowledged, mitigated, resolved). Time to detect, acknowledge, mitigate, and restore calculate in minutes, and so does the share of the error budget consumed.
2. Timeline: build the sequence from logs, alerts, and chat. Record events, not opinions.
3. Contributing Factors: list several factors across tooling, process, communication, design, and monitoring. Avoid a single root cause that names a person.
4. Action Items: each has a type (prevent, detect, mitigate, learn), an owner, and a due date. Track them to completion.
Notes
Blameless means asking what made the action reasonable at the time and what would make the failure harder next time, not who to blame.
Use role names where you can. Do not include customer data, credentials, or other sensitive information.
The example (a 90-minute outage) is a placeholder showing the formulas. Overwrite it.
Yellow cells are inputs. Calculated cells contain formulas.

## Incident Summary
INCIDENT SUMMARY
Enter timestamps as date and time, for example 2026-09-15 14:02.
Item | Entry | Notes
Incident title | Checkout API unavailable | Short, factual
Incident ID | INC-1042
Severity | Sev 2 | Choose from the list
Service | Checkout
Incident commander (role) | On-call engineer
Postmortem author (role) | Service owner
Customer impact | Some customers could not complete checkout for 90 minutes. | Who, how many, what they experienced
How it was detected | Customer reports, then alert on CPU | Monitoring, customers, or another team
Timestamps
Impact started | 2026-09-15 14:02
Detected | 2026-09-15 14:24
Acknowledged | 2026-09-15 14:27
Mitigated (impact stopped) | 2026-09-15 15:10
Resolved (normal service) | 2026-09-15 15:32
Response times (minutes)
Time to detect
Time to acknowledge
Time to mitigate (from detection)
Total duration (start to resolved)
Error budget
SLO (%) | 99.9
Period (days) | 30
Error budget (minutes)
Budget consumed by this incident

## Timeline
TIMELINE
Events in order, from logs, alerts, and chat. Example rows are placeholders.
Time | Event | Source | Notes
2026-09-15 13:40 | Deployment of release 4.18 to all regions began (no canary stage) | Deploy log
2026-09-15 14:02 | Error rate on checkout began rising | Metrics | No alert configured on error rate
2026-09-15 14:24 | Support reported customer complaints; CPU alert fired | Support chat, alert | Detection 22 minutes after impact
2026-09-15 14:27 | On-call engineer acknowledged | Pager
2026-09-15 14:55 | Rollback decision made after review of the release | Chat | Runbook step for rollback was out of date
2026-09-15 15:10 | Rollback complete; error rate returning to normal | Deploy log
2026-09-15 15:32 | Error rate normal for 20 minutes; incident resolved | Metrics

## Contributing Factors
CONTRIBUTING FACTORS
Several factors across categories. Avoid naming a person as the cause. Example rows are placeholders.
ID | Contributing factor | Category | Evidence | What would have prevented or detected it
F1 | No alert on checkout error rate; detection relied on CPU and customers | Monitoring | Timeline: 22 minutes to detect | Alert on request success rate against the SLO
F2 | Release went to all regions at once | Process | Deploy log | Canary release with automatic rollback
F3 | Rollback runbook was out of date | Documentation | Chat: 28 minutes to work out the rollback steps | Runbook rehearsal and ownership
F4 | Load test did not cover the new query path | Testing | Postmortem review of test suite | Add the path to the pre-release performance test

## Action Items
ACTION ITEMS
Each action has a type, an owner, and a due date. Example rows are placeholders.
ID | Action | Type | Linked factor | Owner (role) | Due date | Status | Date completed | Days overdue
A1 | Add alert on checkout request success rate | Detect | F1 | Service owner | 2026-09-25 | Complete | 2026-09-23
A2 | Introduce canary release stage for checkout | Mitigate | F2 | Platform team | 2026-10-15 | In progress
A3 | Update and rehearse the rollback runbook | Prevent | F3 | On-call lead | 2026-10-01 | Open
A4 | Add the new query path to the performance test | Prevent | F4 | QA lead | 2026-10-08 | Open
Formulas:
Days overdue = IF(OR([Due date]="",[Status]="Complete",[Status]="Cancelled"),"",MAX(0,TODAY()-[Due date]))