## How-To
LAST PLANNER WORK PLAN - HOW TO USE
What this workbook is
A working set for the Last Planner System: a six-week lookahead where you screen activities for constraints, a weekly work plan of commitments, and a PPC log that calculates percent plan complete and counts the reasons for misses.
Educational template. It supports a construction team's planning and quality tracking. It is not engineering, legal, contract, building-code, or safety-compliance advice and does not replace your project documents, applicable codes, or the judgment of qualified professionals.
Steps
1. Lookahead: list activities starting in the next six weeks. For each, name any constraint, an owner, and a need-by date. An activity is Ready when it has no constraint or the constraint is Cleared.
2. Weekly Work Plan: for each week, list the assignments crews commit to, using only Ready work. At the end of the week, mark Completed Yes or No, and choose a reason for every No.
3. PPC Log: enter each week's starting date. Planned, Completed, and PPC calculate from the Weekly Work Plan, and the reasons table counts misses by reason.
Notes
PPC measures the reliability of promises, not progress. Track it with schedule progress. Use it to learn as a team, not to rank crews.
Use the first day of the week (for example Monday) consistently in every date column.
The example rows are placeholders showing the formulas. Overwrite them.
Yellow cells are inputs. Calculated cells contain formulas.

## Lookahead
SIX-WEEK LOOKAHEAD
Screen each activity for constraints. Example rows are placeholders.
ID | Activity | Trade | Planned start (week of) | Constraint | Constraint detail | Owner | Need-by date | Status | Ready? | Flag
A01 | Frame corridor walls, level 3 | Framing | 2026-10-12 | None |  | Foreman |  | Cleared
A02 | Rough-in plumbing, level 3 | Plumbing | 2026-10-12 | Materials | Copper fittings due from supplier | Procurement | 2026-10-09 | Open
A03 | Install duct, level 3 ceiling | Mechanical | 2026-10-19 | Design info / RFI | RFI 214 open on duct routing | Project engineer | 2026-10-14 | Open
A04 | Hang drywall, level 3 east | Drywall | 2026-10-19 | Prerequisite work | Above-ceiling inspection needed | Superintendent | 2026-10-16 | Cleared
A05 | Paint level 2 corridors | Paint | 2026-10-26 | Access / space | Floor protection in place | Foreman | 2026-10-22 | Open
Formulas:
Flag = IF(OR([ID]="",[Ready?]="Ready",NOT(ISNUMBER([Need-by date]))),"",IF(TODAY()>[Need-by date],"Late",""))

## Weekly Work Plan
WEEKLY WORK PLAN
One row per assignment. Mark Completed at the end of the week and give a reason for every No.
Week of | Assignment | Trade | Committed? | Completed? | Reason if not completed
2026-10-05 | Frame walls, zone 1 | Framing | Yes | Yes
2026-10-05 | Rough-in electrical, zone 1 | Electrical | Yes | Yes
2026-10-05 | Set duct hangers, zone 1 | Mechanical | Yes | Yes
2026-10-05 | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes
2026-10-05 | Frame walls, zone 2 | Framing | Yes | Yes
2026-10-05 | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes
2026-10-05 | Hang drywall, zone 1 | Drywall | Yes | No | Materials
2026-10-05 | Insulate walls, zone 2 | Insulation | Yes | No | Prerequisite work
2026-10-12 | Frame walls, zone 1 | Framing | Yes | Yes
2026-10-12 | Rough-in electrical, zone 1 | Electrical | Yes | Yes
2026-10-12 | Set duct hangers, zone 1 | Mechanical | Yes | Yes
2026-10-12 | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes
2026-10-12 | Frame walls, zone 2 | Framing | Yes | Yes
2026-10-12 | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes
2026-10-12 | Hang drywall, zone 1 | Drywall | Yes | Yes
2026-10-12 | Insulate walls, zone 2 | Insulation | Yes | No | Design info / RFI
2026-10-19 | Frame walls, zone 1 | Framing | Yes | Yes
2026-10-19 | Rough-in electrical, zone 1 | Electrical | Yes | Yes
2026-10-19 | Set duct hangers, zone 1 | Mechanical | Yes | Yes
2026-10-19 | Rough-in plumbing, zone 2 | Plumbing | Yes | Yes
2026-10-19 | Frame walls, zone 2 | Framing | Yes | Yes
2026-10-19 | Fire-stop penetrations, zone 1 | Fire-stopping | Yes | Yes
2026-10-19 | Hang drywall, zone 1 | Drywall | Yes | No | Labor / crew
2026-10-19 | Insulate walls, zone 2 | Insulation | Yes | Yes

## PPC Log
PERCENT PLAN COMPLETE LOG
Enter each week's start date. Everything else calculates from the Weekly Work Plan.
Week of | Planned | Completed | PPC | Missed | Missed, no reason | Overall PPC
2026-10-05
2026-10-12 | [5 empty] | Reason | Missed assignments
2026-10-19 | [5 empty] | Materials
Prerequisite work
Design info / RFI
Labor / crew
Equipment
Weather
Owner / inspector
Other