## How-To
MANAGEMENT OF CHANGE REGISTER - HOW TO USE
What this workbook is
A working set for management of change (MOC): a request form to describe and review a change, a register that tracks every change through approval to close-out, and a dashboard of open, overdue, and expired items.
Educational template. It supports an asset-management or process-safety team's discussion and documentation. It is not engineering, legal, safety-compliance, or regulatory advice and does not replace your site's procedures, applicable regulations, or the judgment of qualified professionals.
Steps
1. MOC Request Form: describe the change, its technical basis, and the hazard review questions. Print it or copy the fields into your own system.
2. MOC Register: log every change. Record hazard review, approval, document updates, training, and pre-startup review as Yes or No. Days Open, Overdue, Temporary Expired, and Ready to Close calculate automatically.
3. Dashboard: review open changes, overdue items, temporary changes past their end dates, and changes by status and type.
Notes
The example rows are placeholders showing how the formulas behave. Overwrite or delete them. Overdue and expired flags depend on today's date.
Define 'replacement in kind' narrowly and in writing. Give every temporary change an end date and an owner.
Your site's MOC procedure and any applicable regulation take precedence over this template. Edit the checklist to match them.
Yellow cells are inputs. Calculated cells contain formulas.

## MOC Request Form
MANAGEMENT OF CHANGE REQUEST
Complete before the change is made. Keep answers specific.
Item | Entry or prompt
MOC number
Date requested / requester
Area, unit, or equipment
Change type | Permanent, Temporary (give end date and owner), Emergency, or Replacement in kind (define why)
Description of the change | What is being changed, and why?
Technical basis | Design basis, calculations, and drawings affected.
Safety, health, and environmental impact | What new hazards could this create? What existing protections could it affect (alarms, trips, relief, procedures)?
Hazard review method and participants | For example What-If, checklist, or HAZOP node, and who took part (include someone independent of the request).
Documents to update | P&IDs, setpoint lists, operating procedures, maintenance procedures, training material.
Training required | Who must be told or trained, and by when.
Approvals | Names, roles, and dates.
Pre-startup safety review | Who confirmed the change is ready, and how.
Close-out | Date closed, and confirmation that documents are updated and any temporary change is removed.

## MOC Register
MOC REGISTER
Do not delete calculated columns. Example rows are placeholders.
MOC # | Date opened | Description | Area / unit | Change type | Requester | Owner | Hazard review done | Approved | Documents updated | Training complete | PSSR done | Status | Target close date | Date closed | Temporary end date | Days open | Overdue? | Temporary expired? | Ready to close?
MOC-2601 | 2026-08-03 | Replace level transmitter LT-101 with a different range model | Separator area | Permanent | Instrument tech | Process engineer | Yes | Yes | Yes | Yes | Yes | Closed | 2026-08-24 | 2026-08-21
MOC-2602 | 2026-08-20 | Temporary jumper on low-flow trip during compressor commissioning | Compressor station | Temporary | Operations | Operations manager | Yes | Yes | No | Yes | No | Implemented | 2026-09-10 |  | 2026-09-15
MOC-2603 | 2026-09-02 | Change relief valve set pressure after re-rating | Vessel V-200 | Permanent | Process engineer | Process engineer | Yes | No | No | No | No | Open | 2026-10-15
MOC-2604 | 2026-09-12 | Substitute gasket material on hot oil line | Heater area | Permanent | Maintenance | Maintenance lead | No | No | No | No | No | Open | 2026-10-01
Formulas:
Days open = IF([Date opened]="","",IF(ISNUMBER([Date closed]),[Date closed]-[Date opened],TODAY()-[Date opened]))
Overdue? = IF(OR([Date opened]="",ISNUMBER([Date closed]),[Status]="Cancelled"),"",IF(AND(ISNUMBER([Target close date]),TODAY()>[Target close date]),"Overdue",""))
Temporary expired? = IF(AND([Change type]="Temporary",ISNUMBER([Temporary end date]),NOT(ISNUMBER([Date closed])),[Status]<>"Cancelled",TODAY()>[Temporary end date]),"Expired - review","")

## Dashboard
DASHBOARD
Changes logged
Open changes (not closed or cancelled)
Overdue changes
Temporary changes past end date
Closed changes
Changes by status
Open
Approved
Implemented
Closed
Cancelled
Changes by type
Permanent
Temporary
Emergency
Replacement in kind