## How-To
PUBLIC SECTOR IMPROVEMENT CHARTER - HOW TO USE
What this workbook is
A project charter and tracking workbook for a public-service improvement project: define the problem and scope, list milestones and risks, and track benefits by type (cash savings, cost avoidance, capacity released, service improvement).
Educational template. It supports a public-service team's planning and documentation. It is not legal, policy, procurement, or regulatory advice and does not replace your agency's rules, reporting requirements, or the judgment of qualified professionals. Do not enter personal information about residents.
Steps
1. Charter: complete the problem statement, scope, stakeholders, baseline, and target. Get the sponsor's approval before starting.
2. Milestones: list the key dates. Days Overdue calculates for open milestones.
3. Risks: score likelihood and impact (1 to 5). Score and level calculate.
4. Benefits: record each benefit with its type, baseline, target, and actual. Progress and annual value are calculated; the Summary totals annual value by type.
Notes
Keep benefit types separate. Cash savings can be verified in the budget. Capacity released is valuable only if the time is used, so state how it will be redeployed.
The example rows (a permit process project) are placeholders showing the formulas. Overwrite them.
Yellow cells are inputs. Calculated cells contain formulas.

## Charter
PROJECT CHARTER
Complete before work begins. Keep entries brief and specific.
Item | Entry or prompt
Project title | Residential building permit cycle time
Service / process | Residential permits, Building Services
Sponsor
Project lead and team
Problem statement | What is wrong, for whom, how often, and how do we know? Use data.
Public value / why it matters | How does this help residents, businesses, or the agency's mission?
Scope: in | Which steps and cases are included?
Scope: out | What is deliberately excluded?
Legal and policy constraints | Statutes, rules, or agreements that limit what can change.
Stakeholders | Who is affected or must be consulted, including staff and representatives?
Baseline | Current performance, with the measure and period, for example 26.5 business days average over Q2.
Target | The goal, with a date, for example 16 business days by end of Q4.
Balancing measures | What must not get worse, for example error rate, complaints, access for all residents?
Equity and access check | How will we check that the change does not make the service harder to reach?
Resources required
Sponsor approval and date

## Milestones
MILESTONES
Example rows are placeholders.
# | Milestone | Owner | Planned date | Actual date | Status | Days overdue
1 | Map current process and time each step | Project lead | 2026-09-30 | 2026-09-28 | Complete
2 | Analyze return reasons (Pareto) | Analyst | 2026-10-09 |  | In progress
3 | Run improvement event | Facilitator | 2026-10-23 |  | Not started
4 | Pilot new intake checklist | Intake supervisor | 2026-11-20 |  | Not started
Formulas:
Days overdue = IF(OR([Planned date]="",[Status]="Complete",[Status]="Cancelled"),"",MAX(0,TODAY()-[Planned date]))

## Risks
RISKS
Likelihood and impact use a 1 to 5 scale. Example rows are placeholders.
ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Level | Response | Owner
R1 | Staff involvement is limited by workload | 3 | 4 |  |  | Protect time for two reviewers; sponsor confirms priority | Sponsor
R2 | Online checklist is hard to use for some applicants | 3 | 4 |  |  | Test with users, keep paper and in-person options | Project lead
R3 | Rule change alters the process mid-project | 2 | 3 |  |  | Check with legal counsel before each change | Project lead

## Benefits
BENEFITS TRACKING
Record each benefit with its type. Annual value is in dollars where the benefit has a money value.
Benefit | Type | Measure | Baseline | Target | Actual | Progress | Annual value ($) | How it will be verified or used
Faster permit decisions | Service improvement | Business days to permit | 26.5 | 16 | 21 |  |  | Weekly report from the permit system
Less overtime on returns | Cash savings | Overtime hours per quarter | 400 | 250 | 320 |  | 12000 | Payroll records; budget line reduced
Staff time freed from rework | Capacity released | Hours per year | 0 | 1200 | 900 |  | 43200 | Hours redeployed to clear the backlog
Avoided temporary hire | Cost avoidance | Positions not hired | 0 | 1 | 1 |  | 55000 | Approved staffing plan

## Summary
SUMMARY
Milestones listed
Milestones complete
Milestones overdue
High risks
Annual value by benefit type
Cash savings
Cost avoidance
Capacity released
Service improvement measures
Note: report cash savings separately from capacity released.