## How-To
PUNCH LIST AND INSPECTION TRACKER - HOW TO USE
What this workbook is
A set for construction quality tracking: an inspection and test plan (ITP) listing hold, witness, and review points; a punch list with days open and overdue flags; and a dashboard by category.
Educational template. It supports a construction team's planning and quality tracking. It is not engineering, legal, contract, building-code, or safety-compliance advice and does not replace your project documents, applicable codes, or the judgment of qualified professionals.
Steps
1. Inspection Plan: list critical activities with their requirement reference, inspection point type (Hold, Witness, or Review), frequency, responsible person, and acceptance criteria. Agree it with the project team before work starts.
2. Punch List: log each item with location, trade, category, priority, assignee, and due date. Update status as work proceeds. Days Open and Overdue calculate.
3. Dashboard: review counts by status and category, overdue items, and average days open for closed items.
Notes
Keep the ITP and punch list consistent with your contract documents and specifications, which take precedence.
Analyze categories and causes to fix problems at the source on the next project, not just to close items.
The example rows are placeholders showing the formulas. Overwrite them. Overdue flags depend on today's date.
Yellow cells are inputs. Calculated cells contain formulas.

## Inspection Plan
INSPECTION AND TEST PLAN
Example rows are placeholders.
ID | Activity | Requirement / spec reference | Point type | Frequency | Responsible | Acceptance criteria | Records
I01 | Reinforcement before concrete placement | Spec 03 20 00 | Hold | Each pour | Quality manager | Size, spacing, cover, and ties match drawings | Inspection checklist, photos
I02 | Pipe pressure test | Spec 22 05 00 | Witness | Each system | MEP superintendent | Holds test pressure for the specified time with no drop | Test certificate
I03 | Concrete cylinder results | Spec 03 30 00 | Review | Each 7 and 28 days | Quality manager | Strength meets specified minimum | Lab reports
I04 | Drywall finish mock-up | Spec 09 29 00 | Hold | First room, each floor | Drywall foreman and GC | Finish level and joint quality match approved sample | Mock-up sign-off
I05 | Above-ceiling inspection | Spec 01 45 00 | Hold | Each floor | Superintendent | All MEP inspected and signed off before closing ceilings | Inspection checklist
I06 | Door hardware installation | Spec 08 71 00 | Review | 10% sample per floor | Trade foreman | Operation, clearances, and fasteners as specified | Punch sheet

## Punch List
PUNCH LIST
One row per item. Days open and overdue calculate. Example rows are placeholders.
ID | Date found | Location / zone | Trade | Description | Category | Priority | Assigned to | Due date | Status | Date closed | Days open | Overdue?
P001 | 2026-09-14 | Level 2, Room 214 | Paint | Touch-up scuffs on corridor wall | Finishes | Low | Paint foreman | 2026-09-25 | Closed | 2026-09-22
P002 | 2026-09-14 | Level 2, Room 216 | Drywall | Joint crack at ceiling corner | Finishes | Medium | Drywall foreman | 2026-09-28 | Closed | 2026-09-26
P003 | 2026-09-15 | Level 3, Corridor | Electrical | Cover plate missing at outlet | MEP | Medium | Electrical foreman | 2026-09-29 | Closed | 2026-09-27
P004 | 2026-09-15 | Level 3, Room 305 | Carpentry | Door does not latch | Doors and hardware | High | Carpentry foreman | 2026-09-24 | Ready for recheck
P005 | 2026-09-16 | Level 3, Room 308 | Flooring | Gap at transition strip | Finishes | Medium | Flooring foreman | 2026-10-02 | In progress
P006 | 2026-09-17 | Level 1, Lobby | Cleaning | Construction dust on glazing | Cleaning | Low | General cleaner | 2026-10-05 | Open
P007 | 2026-09-17 | Level 1, Mech room | Mechanical | Missing pipe labels | MEP | Medium | Mechanical foreman | 2026-10-01 | Open
P008 | 2026-09-18 | Level 2, Room 220 | Paint | Uneven finish on feature wall | Finishes | High | Paint foreman | 2026-09-26 | Open
Formulas:
Days open = IF([Date found]="","",IF(ISNUMBER([Date closed]),[Date closed]-[Date found],TODAY()-[Date found]))
Overdue? = IF(OR([ID]="",[Status]="Closed",NOT(ISNUMBER([Due date]))),"",IF(TODAY()>[Due date],"Overdue",""))

## Dashboard
DASHBOARD
Items logged
Items open (not closed)
Items closed
Items overdue
Average days open, closed items
Category | Open | Closed | Total
Finishes
MEP
Doors and hardware
Cleaning
Structural
Other